Prolinnova Working Paper 25

Nigeria Prolinnova Programme Development Inception Workshop:

Sharing the Ghana Experiences

Naaminong Karbo

Council for Scientific and Industrial Research–Animal Research Institute, Accra, Ghana

August 2008

Abstract

Promoting Local Innovation (Prolinnova) in Ecologically Oriented Agriculture and Natural Resource Management was initiated by a coalition of international non-governmental organisations (NGOs) in over ten countries. Irrespective of country programmes, one of the common objectives of the network is to build research and development partnerships through recognising local innovation and engaging in joint farmer-led experimentation. In Ghana, Prolinnova partnership activities started in 2003 with a committed group of local NGOs, namely Ecumenical Association for Sustainable Agriculture and Rural Development (ECASARD), the Ghana Organic Agriculture Network (GOAN) and the Association of Church Development Projects (ACDEP) working together with government departments/ institutions such as the Ministry of Food and Agriculture (MoFA) and the Council for Scientific and Industrial Research (CSIR).

For the six years of existence so far (2003–08), the Ghana programme made significant achievements including awareness creation on Prolinnova among current and potential partners, inventory and documentation of local innovations, planning and review workshops at zonal and national levels, training and participation in Prolinnova International Partners Meetings and Workshops including those in the Philippines, Ethiopia, Uganda, Senegal and Ghana. These are done building on the past experiences of the Northern Ghana LEISA Working Group (NGLWG) in the use of participatory approaches in research and development for sustainable rural development.

This paper seeks to bring to the fore the experiences of Ghana as one of the pioneer African country programmes, for sharing with other potential country programmes as Prolinnova continues to grow and scale up and out internationally across countries.

Introduction

Promoting Local Innovation (Prolinnova) in Ecologically Oriented Agriculture and Natural Resource Management was initiated by a coalition of international non-governmental organisations (NGOs) in over ten countries. Prolinnova in general seeks to build on, strengthen and scale up and out participatory research and development (R&D) activities based on farmer-led experimentation and innovation. The continental spread of Prolinnova in Africa covers Ghana, Ethiopia, South Africa, Niger, Sudan, Tanzania and Uganda.

In Ghana, Prolinnova partnership activities started in 2003 with a committed group of local NGOs namely Ecumenical Association for Sustainable Agriculture and Rural Development (ECASARD), Ghana Organic Agriculture Network (GOAN) and Association of Church Development Projects (ACDEP) and government departments/ institutions such as the Ministry of Food and Agriculture (MoFA) and Council for Scientific and Industrial Research (CSIR).

It is gladdening to have big brother Nigeria come into this international hall of fame. Prolinnova Ghana is particularly happy to be party to your programme development. In this, we see the significance of North–South and South–South partnerships which could have far-reaching meaning in our common sub-regional and continental endeavours, amply reflected in ECOWAS (Economic Community of West African States) and NEPAD (New Partnership for Africa’s Development). Indeed, by Prolinnova standards, this is a gesture of true promotion of local innovation in Africa.

This paper presentation therefore seeks to maximise the opportunity in this meeting by sharing Prolinnova–Ghana experiences immediately before the Prolinnova programme emerged, how Ghana got started, the search for things to try in Prolinnova, the results, outcomes and lessons learned to date. It is hoped that any ensuing cross-fertilisation and future linkages could enrich and enhance both country programmes.

Historical perspective

Ghana’s agriculture is largely crop-livestock based with over 60–70 % of the population engaged in it for various types of livelihood. Knowledge generation and transfer systems for the sustainable management of natural resources have come under serious challenges in the past two or three decades, emanating from perceived delivery failures in the face of rising human populations and demand for food, and degradation and erosion of the natural resource base in terms of soil, water, and plant and animal genetic diversity, thus giving permanency to the prevailing rural poverty and disease. The initial question that development workers, researchers and policymakers asked at the time was: Why the high level of non-adoption of technologies generated from research institutions? There was the general feeling that there was something basically wrong with the generation and dissemination approach described as being top-down.

The advocacy for change since the late 1980s required reformulating the question thus: How can development workers, researchers, and other partners catalyse a farmer-led experimentation process for sustainable livelihood development? This actually marked the beginning of the turning point toward farmer-centred R&D activities in northern Ghana, which were realised through the LEISA/PTD Collaborative Research project in partnership with ETC Foundation in the Netherlands.

It was in this period that the philosophy of farmer participation, ‘farmer first’ and ‘farmer in the driving seat’ and the ‘plugging-in principle’ got firmed up in the NGLWG institutional framework. An NGO (ACDEP) became the organising nerve cell of the partners that looked for a strong stakeholder concerted action (Karbo et al 2007, Alebikiya & Karbo 1999) based on building mutual confidence, a common development objective, good rapport with local communities, harnessing official support for collaboration, trust, transparency and effective information flow and mutual respect. All these experiences by the year 2003 appeared to have created fertile ground for the Prolinnova–Ghana seed to germinate and to be nurtured to date.

Getting started for Prolinnova

Considering what has been outlined above, one would have said that Ghana had already got started! However, in PTD thinking, one has to always get started in every new situation where there is learning and sharing. NGLWG had to study the Prolinnova International programme document circulated by our traditional international partners at ETC, Netherlands (the international secretariat of Prolinnova) in various meetings and at committee levels in other zones of the country in order to create an understanding and show of interest to help Ghana develop and own her Prolinnova programme. In northern Ghana, capacities were built in regional PTD/PID teams and trainings held on participatory approaches, behavioural change and other concepts. This indeed created increased awareness and interest in Prolinnova philosophy and potential benefits by local partners, including the ACDEP stations, the Savanna Agricultural Research Institute (CSIR–SARI), the Animal Research Institute (CSIR–ARI), MoFA and the University for Development Studies (UDS) in Tamale, northern Ghana.

The NGLWG team members in northern Ghana were tasked in groups to search the literature for any secondary data and to document the various aspects of local innovation. Similar studies were done in the southern and middle sectors of the country and the reports were fed into various zonal planning workshops. In September 2003, a National Workshop coordinated by ECASARD in Koforidua provided the forum for 30 select representatives of key stakeholders to share the information and then planned for the Prolinnova–Ghana programme.

Looking for things to try

The National Workshop provided the opportunity for the stakeholders to brainstorm and outlined the Prolinnova–Ghana programme objectives. Group work and plenary sessions were used and the suggested objectives clustered into broad areas to include institutional mainstreaming of Prolinnova approaches, capacity building, documentation and dissemination, promotion of genuine farmer groups, gender and policy. The groups also suggested the various activities, roles, time schedules and the resources and inputs required. A team of three persons was tasked to put the document into proper form and submit to the National Steering Committee made up of NGO, MoFA, farmer and research representatives from the zones. For implementation purposes, zonal action plan development needed to fit or contribute to the national Prolinnova–Ghana programme in the same way as the national programme should be seen to contribute to the Prolinnova International programme.

Results, outcomes and lessons

One National Steering Committee with two programmes (northern and southern zones)

During the period 2003–05, the Ghana programme made significant achievements including awareness creation on Prolinnova among current and potential partners, inventory and documentation of local innovations, planning and review workshops at zonal and national levels, training and participation in Prolinnova International Meetings and Workshops in the Philippines, Ethiopia and Uganda. During this period, the national programme also faced challenges because of lack of clear focus and effective coordination and communication with the zonal programme in the north. Budgets were very low for zonal activities and stagnation set in during the period 2004–05. In the given circumstances and motivated by the good prospects of Prolinnova, the National Steering Committee in its 2005 annual meeting resolved unanimously to give autonomy to the two zones to each directly contract, implement and report on activities to the Prolinnova International Secretariat. The National Steering Committee, however, maintained overall management and oversight responsibility of the Ghana programme. The dynamics received the needed support from our international partners.

The northern Ghana Prolinnova programme therefore went on further as a result of the positive development to draw up a strategic plan for the period 2007–10 with the focus on mainstreaming Prolinnova principles in rural development and agricultural research and development programmes of local partners and stakeholders aimed at poverty reduction in northern Ghana.

Local and international partnerships for joint learning and sharing

Participatory video for R&D

As part of the partnership activities, Prolinnova–Ghana benefited from an international training on participatory video (PV) as a powerful tool for empowering farmers and community people to tell their own stories about their innovations and worldviews. The training experience was later replicated in-country by Prolinnova–Ghana playing host to a training session held in northern Ghana in 2004 and facilitated by CSIR–ARI and CECIK (Centre for Cosmovision and Indigenous Knowledge). Prolinnova–Ghana North has since taken this unique opportunity by adapting PV as an R&D tool for enhancing interaction, documentation and dissemination with farmer groups and community members. The CSIR–ARI has employed this tool in crop-livestock integrated studies with communities in the Tolon-Kumbungu District, improved guinea fowl management studies in some communities in the Savelugu-Nanton District and siella mineral lick studies in communities in the Saboba District, all in northern Ghana. In collaboration with the CIDA-funded project Farmer Responsive Mechanisms in Extension and Research (FARMER) in northern Ghana, a PV was also done with the Kolebpour Pig Growers Association in Lawra, Upper West Region.

Some key Prolinnova–Ghana publications for sharing

Apart from the project documents and reports, some publications have been made – though scanty – with assistance from our international partners. Most can be found on the Prolinnova website and include:

- building multi-stakeholder partnerships to promote farmer experimentation and innovation in Ghana

- research to promote farmer innovation: the case of siella mineral lick for livestock in northern Ghana.

Some of our members were also encouraged to contribute papers toward the publication of a booklet on PID to be published by Prolinnova International. The opportunity for researchers in the Ghana programme is that some points could be hauled in towards their promotions at the work place from these publications. In academia, researchers are told to publish or perish! However, it appears more rewarding in my view when such Prolinnova publications can be traced to tangible things and practice in the rural communities.

International Partners Meetings and possibly missed opportunity

The Ghana programme has participated in these annual meetings, including the one in Senegal in early 2007, and indeed successfully hosted the one in early 2008 held in Tamale, Ghana. The beauty of this event is not just reviewing the programme but also the learning of new facilitation approaches and testing the organisational capacities of the host partners. The exposure to field visits to interact with innovators in diverse sociocultural settings and by people from different parts of the world provides each year a new horizon to think about R&D and rural development. The visiting international partners on field trips have eyes in search of what is new. A colleague from Nepal in the recent Ghana location visit remarked that, while in the community trying to see the local innovations, he was only able to see one on his way back when we visited the Paga Crocodile Pond. The innovation was that the local community has been able, with time, to blend local knowledge of managing the pond and crocodiles with present-day tourism for incomes. I agreed with him and started wondering whether there has been any community-led documentation on this innovation.

Reflection on the experience of Ghana having hosted this event revealed that the planned limited number of invitations meant that it did not include many active stakeholders and non-stakeholders in the host country who could have benefited from the proceedings if an appropriate or special session had been provided. Because of the limited budget, there was very minimal or no propaganda! Could this have been a missed opportunity?

Strengthening local collaboration in programme management

For country programmes, it may be appropriate to begin in a small way and then grow. The coordinating NGO and carefully selected multidisciplinary core team serving as the nerve centre should be able to reach out to committed individuals, other NGOs, the research, university and other relevant government organisations such as the Ministry of Agriculture for participation. The Ghana South programme worked closely with the University of Cape Coast, thus involving lecturers and students. The Middle Belt activities were centred on GOAN, an NGO, and expertise drawn from the CSIR–Crop Research Institute.

The Ghana North programme appeared unique in the sense that ACDEP, the coordinating NGO, has its member associations dotted throughout the three northern regions, who could easily reach out to farmers in the field for implementation. The involvement of MoFA in the decentralised District Assembly system was an added strength, since the extension agents live in the communities and play roles in organising the farmer groups. CSIR–SARI, CSIR–ARI and UDS were and are still key local partners providing needed research backstopping and training. Indeed, the partnership in the Ghana programme has grown to involve the participation of other NGOs, such as CECIK and COMPAS (Comparing and Supporting Endogenous Development), who come in with a wealth of knowledge on cosmovision and aspects of social innovations.

True farmer-research-extension linkage

Though research and extension workers may have some knowledge about a commodity or resource, the strength and sustainability of the innovation could go far if they – through the PID process – discover that farmers or community members possess the resources and are doing something about it in their own way and interest and gain some benefits. The interaction process and interest is sustained because the problems and unknowns from the interaction will begin to emerge, requiring tested solutions for a beneficial change. The commitment of a farmer or community to sustain a process is total if only you start with what they know and that which is their felt need. In the case of research and extension workers, more may have to done beyond the personal commitment.

Endogenous resources mobilisation

So far, the local innovations being documented by Prolinnova–Ghana largely involve the mobilisation of resources from within the community. In this vein, farmers are also able to point out what needs to be done but appear challenged financially when payable knowledge or certain resources need to be brought in from outside their system. Funding from outside appears to have the temptation that the farmers or community members lose control over the innovation process, for obvious reasons. The northern Ghana programme is in the process of taking advantage of the opportunity provided by the Prolinnova International Programme to pilot the Local Innovation Support Fund (LISF) in which groups of innovators are empowered financially based on submitted proposals for a sustainable management of such a fund to control the innovation process and derive increased benefits. He who pays the piper calls the tune. Farmers can then mobilise their resources and, in the event, pay for services and demand accountability from such service providers in the value chain!

Transparency and accountability in programme financial management

In general, transparency is a key ingredient in teamwork, the absence of which can negatively affect the prospects of team gelling. This is particularly so when it comes to project finances. The issue here is not about money-driven relationships but to keep team members together and sufficiently informed about what the programme has attracted each time from the submitted plan of activities and budget. In the Ghana North programme, the experience is that the core team members are involved in deciding and drawing up disbursement guidelines. Currently, we are employing the competitive grant scheme, where local partners are encouraged to prioritise the activities and make a proposal within the given budget sealing. These are then reviewed by a panel of core team members and the winners get the funds, implement and report to the ACDEP Secretariat schedule officer supported by a person responsible for monitoring and evaluation. Such reports are also shared at NGLWG team meetings and workshops.

ACDEP, the coordinating NGO, does not hold all the money to its chest! Indeed, Prolinnova programme finances traditionally are often limited in relation to the huge activities out there in the field. No doubt, we are encouraged to look for additional local funding sources to beef up and sustain the process.

Conclusion and suggestions

Prolinnova–Ghana in the community of African country programmes was one of the three pioneers and is almost six years old. The coming into being of the NGLWG before and during the Prolinnova programme and its dynamics with the local coordinating NGO (ACDEP) to date in facilitating farmer-led experimentation could be described or characterised as a local social innovation. It may therefore be suggested that new country programmes consider such an institutional framework and the farmer-first philosophy to innovation. Furthermore, the need is to have a thorough understanding of their country situational analysis for better focusing. Identifying and seating the programme within the relevant sector development policy context of the country aimed at assisting the rural and urban poor could prove rewarding.

Acknowledgements

Appreciation goes to colleagues in the Ghana North programme for nominating me to participate in the Nigeria Prolinnova programme development. I am grateful to the CSIR Management for granting travel permission out of station. The invitation extended to our programme by our Nigerian colleagues for the experience sharing is highly commendable and worth emulating in the sub-region in the context of South–South collaboration. I am also grateful to Ann Waters-Bayer, who kindly accepted to edit the paper and made very useful suggestions.

References

Alebikiya M & Karbo N. 1999. Sustainable agricultural development: the experiences of the Northern Ghana LEISA Working Group (NGLWG). The Savanna Farmer (Newsletter of NGLWG, Tamale, Ghana) 1: 2–6.

Bruce J, Karbo N, Nchor J & Alebikiya M. 2006. Participatory video on ‘siella’ mineral lick: community film viewing and observed changes in ‘siella’ lick development in Wapuli and Chagbani, Saboba-Chereponi District, Ghana. DORCAS Foundation / CSIR / ACDEP, Tamale, Ghana.

Karbo N, Bruce J & Alebikiya M. 2007. Partnership building and the participatory technology development process as a catalyst for development: experiences of the Northern Ghana LEISA Working Group (NGLWG). In: Bruce J et al (eds), Innovative Participatory Research and Development: The Farmer First. Proceedings of the National Conference on Participatory Agricultural Research and Development, held in Tamale, Ghana, pp304–310.

Mainstreaming Community-Led Sustainable Resource Management Sub-Programme (Prolinnova) 2007–2010. ETC EcoCulture proposal to Netherlands Directorate General for International Cooperation (DGIS).

# Footnotes

Invited paper presented at “Meeting of Stakeholders in Agricultural Research and Development to Establish Prolinnova in Nigeria”, 20 August 2008, Kaduna, Nigeria

LEISA: Low-External-Input and Sustainable Agriculture

PTD = Participatory Technology Development

PID = Participatory Innovation Development

CIDA = Canadian International Development Agency